## 📊 Dashboard
🎓 SMART EVENT MANAGEMENT & RESOURCE ALLOCATION SYSTEM ¦ Annual Tech Fest 2025
💰 Total Budget (₹) |  |  |  | ✅ Budget Utilised |  |  | 👥 Volunteers Active | 📋 Tasks Completed
370000 |  |  |  | 76.8% |  |  | 8 | 30%
📊 Budget Allocated vs Spent | [5 empty] | 🍩 Task Status Distribution |  |  | ⚡ Quick Stats
Total Tasks
10
Overdue Tasks
1
Total Volunteers
10
Resources Pending
3
Budget Remaining (₹)
86000
Avg Task Completion
30%
👤 Volunteer Role Coverage
Role | Required | Assigned | Gap | Util% | Status
Stage Manager | 5 | 4 | -1 | 80% | ⚠️ Short
Registration | 8 | 8 | 0 | 100% | ✅ Full
Logistics | 6 | 5 | -1 | 83.33% | ⚠️ Short
AV & Tech | 4 | 3 | -1 | 75% | ⚠️ Short
Security | 10 | 10 | 0 | 100% | ✅ Full
Hospitality | 6 | 4 | -2 | 66.67% | 🔴 Critical
Prizes | 50000 | 42000
Misc | 20000 | 8500

## BudgetTracker
💰 BUDGET TRACKER – Annual Tech Fest 2025
| 370000 | [5 empty] | 76.76%
# | Event | Category | Allocated (₹) | Invoice # | Spent (₹) | Remaining (₹) | % Used | Status | Notes | Category | Allocated | Spent
1 | Annual Tech Fest | Venue & Logistics | 150000 | INV-001 | 112000 | 38000 | 74.67% | Paid |  | Venue & Logistics | 150000 | 112000
2 | Annual Tech Fest | Food & Catering | 80000 | INV-002 | 65000 | 15000 | 81.25% | Paid |  | Food & Catering | 80000 | 65000
3 | Annual Tech Fest | Decoration | 40000 | INV-003 | 38500 | 1500 | 96.25% | Partial |  | Decoration | 40000 | 38500
4 | Annual Tech Fest | Marketing & Promo | 30000 | INV-004 | 18000 | 12000 | 60% | Pending |  | Marketing & Promo | 30000 | 18000
5 | Annual Tech Fest | Prizes & Awards | 50000 | INV-005 | 42000 | 8000 | 84% | Paid |  | Prizes & Awards | 50000 | 42000
6 | Annual Tech Fest | Miscellaneous | 20000 | INV-006 | 8500 | 11500 | 42.5% | Pending |  | Miscellaneous | 20000 | 8500
TOTAL |  |  | 370000 |  | 284000 | 86000 | 76.76%
[10 empty] | Status | Count
[10 empty] | Paid | 3
[10 empty] | Pending | 2
[10 empty] | Partial | 1

## VolunteerAllocation
👥 VOLUNTEER ALLOCATION – Annual Tech Fest 2025
8
ID | Name | Dept | Status | Role | Shift | Check-In | Check-Out | Hours | Event | Notes | Role | Count | Status | Count
V001 | Arjun Sharma | Engineering | Assigned | Stage Manager | Morning | 08:00 | 14:00 | 6 | Annual Tech Fest |  | Stage Manager | 1 | Assigned | 8
V002 | Priya Nair | Arts | Assigned | Decoration | Afternoon | 13:00 | 19:00 | 6 | Annual Tech Fest |  | Decoration | 1 | Standby | 1
V003 | Rohan Mehta | Commerce | Assigned | Registration | Morning | 07:30 | 13:30 | 6 | Annual Tech Fest |  | Registration | 2 | Absent | 1
V004 | Sneha Patel | Science | Standby | AV & Tech | Evening | 18:00 | 22:00 | 4 | Annual Tech Fest |  | AV & Tech | 2
V005 | Kiran Rao | Engineering | Assigned | Logistics | Morning | 08:00 | 16:00 | 8 | Annual Tech Fest |  | Logistics | 1
V006 | Divya Iyer | Medical | Assigned | Hospitality | Afternoon | 12:00 | 20:00 | 8 | Annual Tech Fest |  | Hospitality | 2
V007 | Aditya Kumar | Law | Assigned | Security | Full Day | 07:00 | 21:00 | 14 | Annual Tech Fest |  | Security | 1
V008 | Meera Joshi | Architecture | Assigned | Registration | Morning | 07:30 | 13:30 | 6 | Annual Tech Fest
V009 | Siddharth Roy | Engineering | Absent | AV & Tech | Morning | 08:00 | 14:00 | 6 | Annual Tech Fest
V010 | Ananya Singh | Commerce | Assigned | Hospitality | Evening | 17:00 | 22:00 | 5 | Annual Tech Fest

## TaskTracker
📋 TASK TRACKER – Annual Tech Fest 2025
0.3
ID | Task Name | Owner | Category | Start | Due Date | Status | Priority | % Done | Dependency | Remarks | Notes | Status | Count
T001 | Book Auditorium & Stage | Arjun Sharma | Venue | 01-Sep | 10-Sep | Completed | High | 100% | — | Venue confirmed |  | Not Started | 3
T002 | Design Posters & Banners | Priya Nair | Marketing | 05-Sep | 12-Sep | Completed | High | 100% | T001 | Printed |  | In Progress | 3
T003 | Online Participant Registration | Rohan Mehta | Registration | 08-Sep | 20-Sep | In Progress | High | 70% | — | Portal open |  | Completed | 3
T004 | Coordinate AV Equipment | Siddharth Roy | Technical | 10-Sep | 14-Sep | Overdue | High | 40% | T001 | Escalated |  | Overdue | 1
T005 | Arrange Food & Catering | Divya Iyer | Catering | 10-Sep | 18-Sep | In Progress | Medium | 60% | — | Caterer confirmed |  | On Hold | 0
T006 | Prize Distribution Plan | Aditya Kumar | Coordination | 12-Sep | 15-Sep | Completed | Medium | 100% | — | Done
T007 | Social Media Campaign | Meera Joshi | Marketing | 14-Sep | 20-Sep | In Progress | Medium | 50% | T002 | Running |  | Priority | Count
T008 | Volunteer Briefing Session | Kiran Rao | Logistics | 18-Sep | 19-Sep | Not Started | High | 0% | — | Scheduled |  | High | 6
T009 | Event Day Setup & Rehearsal | Arjun Sharma | Operations | 20-Sep | 20-Sep | Not Started | High | 0% | T008 |  |  | Medium | 3
T010 | Post-Event Report | Sneha Patel | Reporting | 21-Sep | 25-Sep | Not Started | Low | 0% | T009 |  |  | Low | 1

## ResourcePlanning
🗂️ RESOURCE PLANNING – Annual Tech Fest 2025
# | Item | Category | Needed | Available | Shortfall | Unit (₹) | Total (₹) | Supplier | Status | Item | Needed | Available
1 | Folding Chairs | Furniture | 200 | 180 | 20 | 150 | 30000 | BK Traders | Pending | Folding Chairs | 200 | 180
2 | Round Tables | Furniture | 30 | 30 | 0 | 800 | 24000 | BK Traders | Confirmed | Round Tables | 30 | 30
3 | Projectors | AV Equipment | 5 | 4 | 1 | 2500 | 12500 | TechRent Co | Partial | Projectors | 5 | 4
4 | Microphones | AV Equipment | 10 | 8 | 2 | 500 | 5000 | SoundPro | Partial | Microphones | 10 | 8
5 | Extension Cords | Electrical | 25 | 25 | 0 | 200 | 5000 | ElectroMart | Confirmed | Extension Cords | 25 | 25
6 | LED Lights | Decoration | 50 | 40 | 10 | 350 | 17500 | LightHouse | Pending | LED Lights | 50 | 40
7 | Banners (6x4 ft) | Marketing | 15 | 15 | 0 | 700 | 10500 | PrintFast | Confirmed | Banners (6x4 ft) | 15 | 15
8 | First Aid Kits | Safety | 5 | 5 | 0 | 400 | 2000 | MediStore | Confirmed | First Aid Kits | 5 | 5
9 | Water Dispensers | Catering | 8 | 6 | 2 | 1200 | 9600 | AquaServ | Pending | Water Dispensers | 8 | 6
10 | Laptops | AV Equipment | 4 | 3 | 1 | 0 | 0 | College IT | Partial | Laptops | 4 | 3
TOTAL | [6 empty] | 116100
[10 empty] | Category | Total Cost
[10 empty] | Furniture | 54000
[10 empty] | AV Equipment | 17500
[10 empty] | Electrical | 5000
[10 empty] | Decoration | 17500
[10 empty] | Marketing | 10500
[10 empty] | Safety | 2000
[10 empty] | Catering | 9600

## 📈 Pivot Summary
📈 PIVOT SUMMARY – INSIGHTS & ANALYTICS
Budget Utilisation by Category |  |  |  |  | Task & Volunteer Summary
Category | Allocated | Spent | Remaining | % Used | Item | Count | % | Color
Venue & Logistics | 150000 | 112000 | 38000 | 74.67% | Tasks: Completed | 3 | 15.79% | 1E8449
Food & Catering | 80000 | 65000 | 15000 | 81.25% | Tasks: Overdue | 1 | 5.263% | C0392B
Decoration | 40000 | 38500 | 1500 | 96.25% | Tasks: In Progress | 3 | 15.79% | 0D7377
Marketing & Promo | 30000 | 18000 | 12000 | 60% | Vols: Assigned | 8 | 42.11% | 1E8449
Prizes & Awards | 50000 | 42000 | 8000 | 84% | Vols: Absent | 1 | 5.263% | C0392B
Miscellaneous | 20000 | 8500 | 11500 | 42.5% | Resources: Pending | 3 | 15.79% | D35400